## Gantt
Project Gantt Chart
Bars draw themselves from each task's start and end dates. Dark = done, light = remaining.
PROJECT |  | Website Launch |  |  |  | PROJECT START |  | 2027-01-04 |  | TIMELINE STARTS |  | TODAY
PROJECT LEAD |  | Alex Morgan |  |  |  | SCROLL TO WEEK |  | 1 | ← change to move the timeline
# | TASK | OWNER | START | END | DAYS | DONE
1 | Planning
1.1 | Kickoff & goals | Alex | 2027-01-04 | 2027-01-05 |  | 100%
1.2 | Requirements & sitemap | Priya | 2027-01-06 | 2027-01-12 |  | 100%
1.3 | Content inventory | Sam | 2027-01-08 | 2027-01-15 |  | 80%
2 | Design
2.1 | Wireframes | Chris | 2027-01-13 | 2027-01-22 |  | 60%
2.2 | Visual design | Chris | 2027-01-20 | 2027-02-03 |  | 25%
2.3 | Design review & sign-off | Alex | 2027-02-04 | 2027-02-05 |  | 0%
3 | Build
3.1 | Front-end development | Jamie | 2027-02-08 | 2027-02-26 |  | 0%
3.2 | CMS setup & content entry | Sam | 2027-02-15 | 2027-03-03 |  | 0%
3.3 | QA & accessibility testing | Priya | 2027-03-01 | 2027-03-08 |  | 0%
4 | Launch
4.1 | Go-live | Alex | 2027-03-09 | 2027-03-09 |  | 0%
4.2 | Post-launch fixes | Jamie | 2027-03-10 | 2027-03-12 |  | 0%
KEY | Phase rows (1, 2, 3 …) roll up their tasks' dates and % done. Add tasks as 1.4, 2.4 … in blank rows. | [5 empty] | Done |  |  | Remaining | Phase |  | Today
Free template from niftyshelf.com · free for personal & commercial use

## How to use
How to use this Gantt chart
Quick guide
1 | Enter the project name and start date. The timeline begins on the Monday of that week.
2 | Edit task names, owners, start and end dates, and % done. Bars update instantly: dark shows the completed share, light the remaining.
3 | Phase rows (numbered 1, 2, 3) summarize the tasks under them — their dates and % done calculate automatically.
4 | The chart shows 10 weeks at a time. Change 'Scroll to week' (e.g. 5) to move the timeline forward.
5 | To add a task, use a blank row (number it like 2.4) or insert a row inside a phase and copy the formulas from the row above.
6 | Today's date is highlighted in yellow. Print landscape or share as PDF.
Tinted cells are inputs — type over them. White cells calculate automatically.
Works in Excel, Google Sheets (File → Import), Numbers and LibreOffice.
Free template from niftyshelf.com — free for personal and commercial use.