## Tracker
Project Tracker |  | Project name
Status, progress and overdue flags update automatically. | [8 empty] | AS OF
TOTAL TASKS |  | IN PROGRESS |  | DONE |  | BLOCKED |  | OVERDUE |  | COMPLETE
ID | TASK | OWNER | PRIORITY | STATUS | START | DUE | % DONE | PROGRESS | DAYS LEFT | FLAG | NOTES
| Define scope & success metrics | Alex | High | Done | 2027-01-04 | 2027-01-08 | 100% |  |  |  | Signed off by sponsor
| Stakeholder interviews | Priya | Medium | Done | 2027-01-06 | 2027-01-15 | 100%
| Vendor shortlist | Sam | High | In progress | 2027-01-11 | 2027-01-22 | 60% |  |  |  | 3 of 5 demos done
| Budget approval | Alex | High | Blocked | 2027-01-18 | 2027-01-29 | 20% |  |  |  | Waiting on finance
| Data migration plan | Jamie | Medium | In progress | 2027-01-20 | 2027-02-05 | 35%
| Training materials | Chris | Low | Not started | 2027-02-01 | 2027-02-19 | 0%
| Pilot with one team | Priya | Medium | Not started | 2027-02-15 | 2027-03-05 | 0%
| Company-wide rollout | Alex | High | Not started | 2027-03-08 | 2027-03-26 | 0%
Free template from niftyshelf.com · free for personal & commercial use

## How to use
How to use this project tracker
Quick guide
1 | Type the project name, then list one task per row with owner, start and due dates.
2 | Pick a Priority and Status from the dropdowns and update % done as work moves.
3 | The progress bar, days left and flags (Overdue / Due soon / Done) update automatically, using today's date.
4 | The cards at the top count tasks by status and show overall % complete.
5 | Use the filter arrows in the header row to show one owner, status or priority.
Tinted cells are inputs — type over them. White cells calculate automatically.
Works in Excel, Google Sheets (File → Import), Numbers and LibreOffice.
Free template from niftyshelf.com — free for personal and commercial use.